## Work Items
Project Planner
S.No | Work Item | Start Date | End Date | Status | Est. Days
1 | Requirements Gathering |  |  | Done
2 | Wireframe UI Design |  |  | Done
3 | Scoping and Identifying Entitiy Classes |  |  | done
4 | Create Application Architecture - Clean Architecture | 2023-08-07 | 2023-08-07 |  | 1
5 | Create Project Structure | 2023-08-07 | 2023-08-07 |  | 1
6 | Implement the Domain Layer - Creating Entity Classess, Interfaces and Impl | 2023-08-08 | 2023-08-10 |  | 3
7 | Implement the Data Layer using EF Code First Approach | 2023-08-11 | 2023-08-16 |  | 4
8 | Design Web UI using MVC Core | 2023-08-17 | 2023-08-25 |  | 7
9 | Integrate UI, Domain and Data layers | 2023-08-28 | 2023-08-28 |  | 1
10 | Testing and Debugging | 2023-08-29 | 2023-08-29 |  | 1
11 | Deployment | 2023-08-30 | 2023-08-30 |  | 1
12 | Presentation | 2023-08-31 | 2023-08-31 |  | 1
13
14
15
16
17
18
19